## CE Work Orders
Work Order # | CE Work Order # | Installation | Facility Number | Facility Name | Room/Area | Request DateTime | Requesting Organization | Work Category | Trade | Priority Code | Problem Description | Requested Action | Mission Impact | Status | Assigned Shop | Actions Taken | Completion Date
USSPC-FAC-2026-0001 | TRIRIGA-26-12001 | Peterson SFB | 105 | Communications Hub 105 | Cable Vault | 2026-02-01 0000Z | USSPACECOM J3 | Urgent | Lighting | 3 | Exit sign lamp out at emergency egress route. | Replace exit sign lamp and verify illumination. | Yes – affects classified processing environment. | Submitted | CE Lighting
USSPC-FAC-2026-0002 | TRIRIGA-26-12002 | Peterson SFB | 3 | Power Generation Facility 3 | Control Room | 2026-02-01 0015Z | USSPACECOM J2 | Urgent | Electrical | 2 | Transformer humming abnormally; oil temperature gauge reading high. | Inspect transformer; sample oil and assess condition. | No – quality of life issue; no mission degradation. | In Progress | CE Electrical
USSPC-FAC-2026-0003 | TRIRIGA-26-12003 | Vandenberg SFB | 77 | Secure Data Facility 77 | Server Room B | 2026-02-01 0310Z | USSPACECOM J2 | Urgent | Electrical | 2 | Intermittent power loss to operator consoles on ops floor. | Troubleshoot intermittent power issue and restore stable supply. | No – aesthetic/comfort issue only. | Approved | CE Electrical
USSPC-FAC-2026-0004 | TRIRIGA-26-12004 | Peterson SFB | 105 | Communications Hub 105 | Antenna Equipment Room | 2026-02-01 0330Z | USSPACECOM J2 | Routine | Electrical | 4 | Neutral-to-ground voltage elevated at 7V; exceeding acceptable limits. | Investigate elevated neutral-to-ground voltage and correct. | No – routine upkeep; no operational impact. | Completed | CE Electrical | Responded to work order. Found ATS control board fault. Cleaned and re-torqued neutral bus connections. Thermal scan confirmed normal temperatures. Completed per NEC requirements. | 2026-02-15
USSPC-FAC-2026-0005 | TRIRIGA-26-12005 | Vandenberg SFB | 51 | Launch Operations Building 51 | Roof | 2026-02-01 0535Z | USSPACECOM J2 | Preventive Maintenance | ESS | 4 | Preventive maintenance on access control system firmware and hardware. | Repair intercom system and test two-way communication. | No – preventive maintenance. | Scheduled | CE ESS
USSPC-FAC-2026-0006 | TRIRIGA-26-12006 | Vandenberg SFB | 134 | Range Control Facility 134 | Exterior HVAC Pad | 2026-02-01 0615Z | USSPACECOM J4 | Urgent | Lighting | 2 | Flickering fluorescent fixtures in office area causing occupant complaints. | Replace flickering fixtures with new lamps or ballasts. | No – personnel safety concern. | Approved | CE Lighting
USSPC-FAC-2026-0007 | TRIRIGA-26-12007 | Peterson SFB | 88 | Data Processing Facility 88 | Battery Room | 2026-02-01 0815Z | USSPACECOM J2 | Urgent | ESS | 2 | CCTV camera 25 offline; no video feed to security monitoring. | Troubleshoot camera fault and restore video feed. | No – personnel safety concern. | Completed | CE ESS | Technician inspected ESS components. Identified controller firmware communication error. Replaced network cable and verified video feed. System tested end-to-end; all access points verified operational. Security notified of restoration. | 2026-02-02
USSPC-FAC-2026-0008 | TRIRIGA-26-12008 | Buckley SFB | 312 | Operations Annex 312 | Secure Entry Vestibule | 2026-02-01 1005Z | USSPACECOM J6 | Urgent | ESS | 2 | Card reader database sync failure; stale credential data. | Resolve database sync issue and verify credential data. | Yes – impacts secure communications capability. | Approved | CE ESS
USSPC-FAC-2026-0009 | TRIRIGA-26-12009 | Peterson SFB | 42 | Administrative Building 42 | Restroom A | 2026-02-01 1705Z | USSPACECOM J4 | Urgent | Electrical | 3 | Power monitoring system reporting harmonics above threshold on critical bus. | Install harmonic filtering or identify harmonic source. | Yes – supports satellite uplink equipment. | Completed | CE Electrical | Responded to work order. Discovered failed UPS battery cells in string 2. Redistributed loads and labeled circuits per NEC 408.4. Thermal scan confirmed normal temperatures. Completed per NEC requirements. | 2026-02-04
USSPC-FAC-2026-0010 | TRIRIGA-26-12010 | Peterson SFB | 105 | Communications Hub 105 | Ground Floor Lobby | 2026-02-01 1810Z | USSPACECOM J3 | Urgent | ESS | 2 | Anti-tailgating sensor malfunctioning at secure entry. | Repair anti-tailgating sensor and recalibrate. | Yes – impacts launch operations support systems. | In Progress | CE ESS
USSPC-FAC-2026-0011 | TRIRIGA-26-12011 | Peterson SFB | 42 | Administrative Building 42 | Breakroom | 2026-02-01 1900Z | USSPACECOM J6 | Urgent | HVAC | 2 | Refrigerant leak suspected on split system unit; ice formation on suction line. | Locate and repair refrigerant leak; recharge system to spec. | Yes – delayed access to mission operations spaces. | Approved | CE HVAC
USSPC-FAC-2026-0012 | TRIRIGA-26-12012 | Peterson SFB | 88 | Data Processing Facility 88 | Server Hall B | 2026-02-01 2040Z | USSPACECOM J4 | Routine | Fire Protection | 3 | Fire door held open with unauthorized wedge; closer mechanism degraded. | Repair fire door closer mechanism and verify self-closing. | Yes – mission-critical data processing environment. | Completed | CE Fire Protection | Responded and placed system in test mode. Discovered failed fire alarm control module. Replaced controller relay and tested pump start sequence. Fire alarm panel cleared; all devices verified operational. | 2026-02-15
USSPC-FAC-2026-0013 | TRIRIGA-26-12013 | Vandenberg SFB | 77 | Secure Data Facility 77 | Battery Room | 2026-02-01 2045Z | USSPACECOM J2 | Urgent | Lighting | 3 | Exterior security lighting inoperative on building north side. | Repair exterior security lighting and verify coverage. | Yes – impacts launch operations support systems. | Approved | CE Lighting
USSPC-FAC-2026-0014 | TRIRIGA-26-12014 | Buckley SFB | 180 | Mission Support Facility 180 | Exterior Pad | 2026-02-02 0125Z | USSPACECOM J2 | Urgent | Fire Protection | 2 | Clean agent suppression system showing low bottle pressure. | Recharge or replace clean agent suppression bottles. | Yes – loss of backup power to mission facilities. | In Progress | CE Fire Protection
USSPC-FAC-2026-0015 | TRIRIGA-26-12015 | Peterson SFB | 3 | Power Generation Facility 3 | Generator Bay 2 | 2026-02-02 0300Z | USSPACECOM J4 | Emergency | Plumbing | 1 | Restroom fixture running continuously; float valve suspected faulty. | Replace fixture valve components and verify operation. | Yes – degrades mission operations center readiness. | Approved | CE Plumbing
USSPC-FAC-2026-0016 | TRIRIGA-26-12016 | Schriever SFB | 302 | Communications Facility 302 | Cable Tray Area | 2026-02-02 0530Z | USSPACECOM J3 | Emergency | Electrical | 1 | Frequent breaker trips observed on mission operations power panel E-13. | Inspect panel, identify overload condition, and replace faulty breakers. | Yes – mission-critical data processing environment. | In Progress | CE Electrical
USSPC-FAC-2026-0017 | TRIRIGA-26-12017 | Buckley SFB | 312 | Operations Annex 312 | Rooftop | 2026-02-02 0540Z | USSPACECOM J2 | Routine | Structural | 3 | Concrete spalling on loading dock surface; rebar partially exposed. | Patch spalled concrete and apply protective coating. | Potential – risk to nearby equipment if condition worsens. | Submitted | CE Structural
USSPC-FAC-2026-0018 | TRIRIGA-26-12018 | Peterson SFB | 145 | Operations Building 145 | Mechanical Room | 2026-02-02 0645Z | USSPACECOM J2 | Urgent | Structural | 3 | Crack observed in exterior wall exceeding 1/4 inch width; moisture intrusion suspected. | Assess crack, seal exterior, and monitor for propagation. | Yes – affects continuous space surveillance mission. | In Progress | CE Structural
USSPC-FAC-2026-0019 | TRIRIGA-26-12019 | Buckley SFB | 180 | Mission Support Facility 180 | Restroom Corridor | 2026-02-02 0750Z | USSPACECOM J2 | Emergency | Fire Protection | 1 | Fire suppression control panel reporting system fault. | Inspect and restore fire suppression system functionality. | Yes – mission-critical data processing environment. | Completed | CE Fire Protection | Responded and placed system in test mode. Found fire pump controller relay failure. Replaced controller relay and tested pump start sequence. Fire alarm panel cleared; all devices verified operational. | 2026-02-03
USSPC-FAC-2026-0020 | TRIRIGA-26-12020 | Peterson SFB | 198 | Operations Building 198 | Loading Area | 2026-02-02 0855Z | USSPACECOM J3 | Preventive Maintenance | Lighting | 4 | Preventive maintenance on exterior lighting and photocell replacement. | Replace emergency lighting battery unit and test. | No – preventive maintenance. | Approved | CE Lighting
USSPC-FAC-2026-0021 | TRIRIGA-26-12021 | Schriever SFB | 302 | Communications Facility 302 | Electrical Room | 2026-02-02 1145Z | USSPACECOM J6 | Urgent | Plumbing | 2 | Domestic water pressure low throughout facility; measured at 22 PSI vs 60 PSI normal. | Investigate low water pressure and restore to normal. | No – aesthetic/comfort issue only. | Approved | CE Plumbing
USSPC-FAC-2026-0022 | TRIRIGA-26-12022 | Buckley SFB | 180 | Mission Support Facility 180 | Main Hall | 2026-02-02 1320Z | USSPACECOM J2 | Routine | Structural | 3 | Handrail loose on exterior stairway; anchor bolts corroded. | Secure handrail; replace corroded anchor bolts. | Potential – potential cascade failure if not addressed. | Submitted | CE Structural
USSPC-FAC-2026-0023 | TRIRIGA-26-12023 | Peterson SFB | 198 | Operations Building 198 | Lobby | 2026-02-02 1535Z | USSPACECOM J6 | Urgent | Lighting | 3 | Daylight harvesting sensors out of calibration; lights full on during daylight. | Recalibrate daylight harvesting sensors. | No – general facility maintenance. | Submitted | CE Lighting
USSPC-FAC-2026-0024 | TRIRIGA-26-12024 | Schriever SFB | 302 | Communications Facility 302 | Electrical Room | 2026-02-02 1620Z | USSPACECOM J6 | Routine | ESS | 3 | Motion sensor PIR detector degraded; detection range reduced. | Replace PIR motion sensor and verify detection coverage. | No – general facility maintenance. | Submitted | CE ESS
USSPC-FAC-2026-0025 | TRIRIGA-26-12025 | Schriever SFB | 400 | Satellite Operations Facility 400 | Ground Station Control Room | 2026-02-02 1710Z | USSPACECOM J6 | Preventive Maintenance | Lighting | 4 | Preventive maintenance on exterior lighting and photocell replacement. | Replace emergency lighting battery unit and test. | No – preventive maintenance. | Completed | CE Lighting | Technician inspected lighting system. Found ballast failure in fluorescent fixture. Replaced ballast and installed new lamps. All fixtures verified operational; light levels measured and within IES standards. | 2026-02-11
USSPC-FAC-2026-0026 | TRIRIGA-26-12026 | Peterson SFB | 42 | Administrative Building 42 | Parking Structure | 2026-02-02 1810Z | USSPACECOM J3 | Urgent | Lighting | 2 | Emergency lighting battery unit failed self-test; no backup illumination. | Replace emergency lighting battery unit and test. | Yes – supports satellite uplink equipment. | Completed | CE Lighting | Arrived on-site and assessed lighting condition. Found corroded fixture wiring connection. Repaired wiring connection and verified circuit integrity. Area lighting restored to full operation. | 2026-02-06
USSPC-FAC-2026-0027 | TRIRIGA-26-12027 | Peterson SFB | 42 | Administrative Building 42 | Records Room | 2026-02-02 1855Z | USSPACECOM J3 | Emergency | Plumbing | 2 | Hot water temperature at fixtures below acceptable range; measured 90°F. | Diagnose hot water temperature issue and adjust or repair. | Yes – affects missile warning operations continuity. | Completed | CE Plumbing | Technician inspected and identified Discovered dried-out P-trap in floor drain. Installed hammer arrestors at offending fixtures. System pressure tested and verified at normal operating range. No further leaks observed. | 2026-02-03
USSPC-FAC-2026-0028 | TRIRIGA-26-12028 | Peterson SFB | 105 | Communications Hub 105 | Antenna Equipment Room | 2026-02-02 1900Z | USSPACECOM J2 | Urgent | Power Production | 3 | Generator ran but did not achieve rated output; voltage droop under load. | Troubleshoot generator output issue and restore rated capacity. | No – personnel safety and usability concern. | Approved | CE Power Production
USSPC-FAC-2026-0029 | TRIRIGA-26-12029 | Peterson SFB | 105 | Communications Hub 105 | HVAC Plenum | 2026-02-02 2005Z | USSPACECOM J4 | Routine | Fire Protection | 3 | False alarm activations from smoke detector zone 8; third occurrence this month. | Troubleshoot false alarm source and replace faulty detector. | No – general facility maintenance. | In Progress | CE Fire Protection
USSPC-FAC-2026-0030 | TRIRIGA-26-12030 | Peterson SFB | 210 | Operations Building 210 | Mechanical Penthouse | 2026-02-02 2050Z | USSPACECOM J3 | Routine | ESS | 4 | Access control panel communication fault; door status unknown. | Restore communication between access control panel and host. | Potential – potential cascade failure if not addressed. | Submitted | CE ESS
USSPC-FAC-2026-0031 | TRIRIGA-26-12031 | Vandenberg SFB | 77 | Secure Data Facility 77 | Battery Room | 2026-02-02 2250Z | USSPACECOM J3 | Urgent | Lighting | 3 | Lighting control system not responding to occupancy sensors in zone 11. | Troubleshoot occupancy sensor control and restore function. | No – quality of life issue; no mission degradation. | In Progress | CE Lighting
USSPC-FAC-2026-0032 | TRIRIGA-26-12032 | Peterson SFB | 88 | Data Processing Facility 88 | Server Hall A | 2026-02-02 2255Z | USSPACECOM J3 | Urgent | Plumbing | 2 | Condensate drain line from AHU clogged; water collecting in drain pan. | Clear condensate drain line and treat to prevent recurrence. | Yes – supports satellite uplink equipment. | Approved | CE Plumbing
USSPC-FAC-2026-0033 | TRIRIGA-26-12033 | Buckley SFB | 312 | Operations Annex 312 | Server Closet | 2026-02-02 2255Z | USSPACECOM J2 | Routine | Lighting | 3 | Exit sign lamp out at emergency egress route. | Replace exit sign lamp and verify illumination. | Yes – supports space domain awareness operations. | Approved | CE Lighting
USSPC-FAC-2026-0034 | TRIRIGA-26-12034 | Peterson SFB | 198 | Operations Building 198 | Loading Area | 2026-02-03 0250Z | USSPACECOM J2 | Urgent | Structural | 3 | Door frame misaligned; secure door not seating properly in frame. | Adjust or replace door frame hardware for proper operation. | No – personnel safety concern. | Approved | CE Structural
USSPC-FAC-2026-0035 | TRIRIGA-26-12035 | Peterson SFB | 145 | Operations Building 145 | Conference Room 3 | 2026-02-03 0340Z | USSPACECOM J2 | Routine | Structural | 3 | Retaining wall showing lateral displacement; drainage weeps clogged. | Clear retaining wall weeps and assess lateral stability. | No – aesthetic/comfort issue only. | Submitted | CE Structural
USSPC-FAC-2026-0036 | TRIRIGA-26-12036 | Schriever SFB | 400 | Satellite Operations Facility 400 | Antenna Maintenance Area | 2026-02-03 0655Z | USSPACECOM J6 | Emergency | ESS | 2 | Perimeter fence detection system reporting intermittent faults. | Troubleshoot perimeter detection system and restore monitoring. | Yes – affects classified processing environment. | Completed | CE ESS | Technician inspected ESS components. Found door lock solenoid failure. Replaced card reader assembly and programmed to system. System tested end-to-end; all access points verified operational. Security notified of restoration. | 2026-02-04
USSPC-FAC-2026-0037 | TRIRIGA-26-12037 | Vandenberg SFB | 51 | Launch Operations Building 51 | Control Room | 2026-02-03 0835Z | USSPACECOM J4 | Routine | Lighting | 3 | Exit sign lamp out at emergency egress route. | Replace exit sign lamp and verify illumination. | No – quality of life issue; no mission degradation. | In Progress | CE Lighting
USSPC-FAC-2026-0038 | TRIRIGA-26-12038 | Vandenberg SFB | 77 | Secure Data Facility 77 | Mechanical Room | 2026-02-03 0845Z | USSPACECOM J4 | Urgent | Power Production | 2 | Generator ran but did not achieve rated output; voltage droop under load. | Troubleshoot generator output issue and restore rated capacity. | Yes – degrades mission operations center readiness. | Approved | CE Power Production
USSPC-FAC-2026-0039 | TRIRIGA-26-12039 | Peterson SFB | 210 | Operations Building 210 | Ops Floor | 2026-02-03 1030Z | USSPACECOM J3 | Urgent | Plumbing | 2 | Floor drain backing up intermittently in mechanical room. | Clear floor drain blockage and verify flow. | No – preventive maintenance. | Completed | CE Plumbing | Technician inspected and identified Found corroded pipe fitting at joint. Replaced pressure regulator and set to 55 PSI. System pressure tested and verified at normal operating range. No further leaks observed. | 2026-02-06
USSPC-FAC-2026-0040 | TRIRIGA-26-12040 | Schriever SFB | 400 | Satellite Operations Facility 400 | Equipment Bay | 2026-02-03 1035Z | USSPACECOM J4 | Urgent | Plumbing | 2 | Water hammer occurring in supply piping when fixtures cycle. | Install water hammer arrestors and secure piping supports. | No – administrative area; no mission systems affected. | Approved | CE Plumbing
USSPC-FAC-2026-0041 | TRIRIGA-26-12041 | Peterson SFB | 3 | Power Generation Facility 3 | Generator Bay 1 | 2026-02-03 1240Z | USSPACECOM J3 | Routine | Lighting | 4 | Parking lot light pole 6 dark; ballast or photocell suspected. | Replace ballast or photocell and restore pole light operation. | No – aesthetic/comfort issue only. | Submitted | CE Lighting
USSPC-FAC-2026-0042 | TRIRIGA-26-12042 | Peterson SFB | 3 | Power Generation Facility 3 | Switchgear Room | 2026-02-03 1330Z | USSPACECOM J4 | Routine | ESS | 3 | Intercom system non-functional at entry control point. | Repair intercom system and test two-way communication. | No – general facility maintenance. | Submitted | CE ESS
USSPC-FAC-2026-0043 | TRIRIGA-26-12043 | Schriever SFB | 302 | Communications Facility 302 | Electrical Room | 2026-02-03 1410Z | USSPACECOM J6 | Routine | ESS | 3 | Anti-tailgating sensor malfunctioning at secure entry. | Repair anti-tailgating sensor and recalibrate. | No – personnel safety concern. | Completed | CE ESS | Responded and coordinated with security forces. Identified controller firmware communication error. Replaced network cable and verified video feed. Credentials tested at affected entry points; full functionality confirmed. | 2026-02-10
USSPC-FAC-2026-0044 | TRIRIGA-26-12044 | Schriever SFB | 302 | Communications Facility 302 | Roof | 2026-02-03 1415Z | USSPACECOM J4 | Routine | Lighting | 4 | Exterior security lighting inoperative on building north side. | Repair exterior security lighting and verify coverage. | No – routine upkeep; no operational impact. | Completed | CE Lighting | Arrived on-site and assessed lighting condition. Identified tripped lighting circuit breaker. Reset breaker and identified root cause; labeled circuit. Area lighting restored to full operation. | 2026-02-08
USSPC-FAC-2026-0045 | TRIRIGA-26-12045 | Buckley SFB | 312 | Operations Annex 312 | Server Closet | 2026-02-03 1615Z | USSPACECOM J6 | Emergency | Power Production | 2 | Battery charger for generator starting batteries showing fault. | Replace battery charger and verify starting battery voltage. | Yes – loss of backup power to mission facilities. | In Progress | CE Power Production
USSPC-FAC-2026-0046 | TRIRIGA-26-12046 | Peterson SFB | 3 | Power Generation Facility 3 | Transfer Switch Room | 2026-02-03 1840Z | USSPACECOM J4 | Urgent | Electrical | 2 | Voltage sag measured at distribution panel; equipment brownouts reported. | Investigate voltage sag source and correct distribution issue. | Yes – degrades mission operations center readiness. | Approved | CE Electrical
USSPC-FAC-2026-0047 | TRIRIGA-26-12047 | Vandenberg SFB | 77 | Secure Data Facility 77 | Battery Room | 2026-02-03 2000Z | USSPACECOM J6 | Routine | Electrical | 4 | Phase imbalance measured at 14% on main distribution panel. | Balance phase loading on main distribution panel. | Potential – risk to nearby equipment if condition worsens. | Submitted | CE Electrical
USSPC-FAC-2026-0048 | TRIRIGA-26-12048 | Peterson SFB | 145 | Operations Building 145 | Mechanical Room | 2026-02-03 2005Z | USSPACECOM J2 | Preventive Maintenance | Power Production | 4 | Quarterly fuel sampling and polishing service. | Perform monthly generator run test and document results. | No – preventive maintenance. | Approved | CE Power Production
USSPC-FAC-2026-0049 | TRIRIGA-26-12049 | Peterson SFB | 3 | Power Generation Facility 3 | Switchgear Room | 2026-02-03 2325Z | USSPACECOM J4 | Preventive Maintenance | Electrical | 4 | Preventive maintenance due on UPS battery string per manufacturer schedule. | De-energize and inspect switchgear; address arc flash indicators. | No – preventive maintenance. | Completed | CE Electrical | Technician de-energized and inspected per NFPA 70E. Found ATS control board fault. Tested and documented all protective device settings. System re-energized and tested under load; operating normally. | 2026-02-21
USSPC-FAC-2026-0050 | TRIRIGA-26-12050 | Buckley SFB | 180 | Mission Support Facility 180 | Exterior Pad | 2026-02-04 0140Z | USSPACECOM J4 | Urgent | Fire Protection | 3 | Sprinkler system pressure gauge reading below minimum; 44 PSI observed. | Investigate low sprinkler pressure and restore to minimum. | No – general facility maintenance. | In Progress | CE Fire Protection
USSPC-FAC-2026-0051 | TRIRIGA-26-12051 | Peterson SFB | 145 | Operations Building 145 | Restroom Corridor | 2026-02-04 0245Z | USSPACECOM J2 | Urgent | Lighting | 2 | Daylight harvesting sensors out of calibration; lights full on during daylight. | Recalibrate daylight harvesting sensors. | No – personnel safety and usability concern. | Approved | CE Lighting
USSPC-FAC-2026-0052 | TRIRIGA-26-12052 | Schriever SFB | 220 | Mission Support Building 220 | Corridor B | 2026-02-04 0425Z | USSPACECOM J6 | Emergency | Fire Protection | 2 | Fire suppression control panel reporting system fault. | Inspect and restore fire suppression system functionality. | Yes – affects classified processing environment. | Completed | CE Fire Protection | Responded and placed system in test mode. Identified leaking sprinkler system check valve. Replaced pull station and tested alarm signal to panel. Fire alarm panel cleared; all devices verified operational. | 2026-02-05
USSPC-FAC-2026-0053 | TRIRIGA-26-12053 | Buckley SFB | 312 | Operations Annex 312 | Secure Entry Vestibule | 2026-02-04 1100Z | USSPACECOM J6 | Urgent | Electrical | 2 | Ground fault detected on branch circuit serving critical equipment. | Locate and clear ground fault on branch circuit. | Yes – delayed access to mission operations spaces. | In Progress | CE Electrical
USSPC-FAC-2026-0054 | TRIRIGA-26-12054 | Buckley SFB | 180 | Mission Support Facility 180 | Restroom Corridor | 2026-02-04 1125Z | USSPACECOM J4 | Urgent | Power Production | 2 | Block heater on standby generator non-functional; engine cold. | Repair or replace block heater and verify engine preheat. | Yes – supports satellite command and control systems. | Submitted | CE Power Production
USSPC-FAC-2026-0055 | TRIRIGA-26-12055 | Schriever SFB | 302 | Communications Facility 302 | Equipment Room 2 | 2026-02-04 1135Z | USSPACECOM J3 | Urgent | Lighting | 2 | Parking lot light pole 20 dark; ballast or photocell suspected. | Replace ballast or photocell and restore pole light operation. | Yes – supports space domain awareness operations. | Submitted | CE Lighting
USSPC-FAC-2026-0056 | TRIRIGA-26-12056 | Peterson SFB | 198 | Operations Building 198 | Mechanical Room | 2026-02-04 1615Z | USSPACECOM J6 | Emergency | Plumbing | 2 | Water hammer occurring in supply piping when fixtures cycle. | Install water hammer arrestors and secure piping supports. | Yes – impacts secure communications capability. | In Progress | CE Plumbing
USSPC-FAC-2026-0057 | TRIRIGA-26-12057 | Peterson SFB | 42 | Administrative Building 42 | Parking Structure | 2026-02-04 1920Z | USSPACECOM J3 | Routine | ESS | 4 | Intrusion detection sensor reporting false alarms in zone 12. | Investigate false alarm source; adjust or replace sensor. | Potential – risk to nearby equipment if condition worsens. | Completed | CE ESS | Technician inspected ESS components. Identified controller firmware communication error. Cleaned sensor lens and recalibrated detection zone. System tested end-to-end; all access points verified operational. Security notified of restoration. | 2026-02-20
USSPC-FAC-2026-0058 | TRIRIGA-26-12058 | Vandenberg SFB | 134 | Range Control Facility 134 | Ops Floor | 2026-02-04 2125Z | USSPACECOM J2 | Routine | HVAC | 3 | Return air temperature sensor reading erratic values; zone control degraded. | Replace return air temperature sensor and recalibrate. | Yes – delayed access to mission operations spaces. | In Progress | CE HVAC
USSPC-FAC-2026-0059 | TRIRIGA-26-12059 | Peterson SFB | 105 | Communications Hub 105 | Roof Antenna Platform | 2026-02-04 2205Z | USSPACECOM J2 | Routine | Structural | 3 | Concrete spalling on loading dock surface; rebar partially exposed. | Patch spalled concrete and apply protective coating. | No – aesthetic/comfort issue only. | Submitted | CE Structural
USSPC-FAC-2026-0060 | TRIRIGA-26-12060 | Vandenberg SFB | 77 | Secure Data Facility 77 | Server Room A | 2026-02-04 2325Z | USSPACECOM J4 | Urgent | Plumbing | 3 | Floor drain backing up intermittently in mechanical room. | Clear floor drain blockage and verify flow. | No – quality of life issue; no mission degradation. | In Progress | CE Plumbing
USSPC-FAC-2026-0061 | TRIRIGA-26-12061 | Vandenberg SFB | 77 | Secure Data Facility 77 | Server Room A | 2026-02-05 0310Z | USSPACECOM J3 | Emergency | ESS | 2 | Perimeter fence detection system reporting intermittent faults. | Troubleshoot perimeter detection system and restore monitoring. | Yes – supports satellite uplink equipment. | Completed | CE ESS | Responded and coordinated with security forces. Found failed card reader magnetic head. Replaced card reader assembly and programmed to system. Credentials tested at affected entry points; full functionality confirmed. | 2026-02-07
USSPC-FAC-2026-0062 | TRIRIGA-26-12062 | Peterson SFB | 198 | Operations Building 198 | Lobby | 2026-02-05 0345Z | USSPACECOM J4 | Urgent | ESS | 2 | Anti-tailgating sensor malfunctioning at secure entry. | Repair anti-tailgating sensor and recalibrate. | Yes – degrades mission operations center readiness. | Submitted | CE ESS
USSPC-FAC-2026-0063 | TRIRIGA-26-12063 | Schriever SFB | 220 | Mission Support Building 220 | Corridor B | 2026-02-05 0415Z | USSPACECOM J2 | Urgent | Structural | 3 | Door frame misaligned; secure door not seating properly in frame. | Adjust or replace door frame hardware for proper operation. | Potential – potential cascade failure if not addressed. | In Progress | CE Structural
USSPC-FAC-2026-0064 | TRIRIGA-26-12064 | Peterson SFB | 3 | Power Generation Facility 3 | Control Room | 2026-02-05 0435Z | USSPACECOM J2 | Routine | Lighting | 3 | High-bay lights in warehouse area cycling on and off intermittently. | Troubleshoot high-bay fixture cycling and correct. | Yes – impacts secure communications capability. | Approved | CE Lighting
USSPC-FAC-2026-0065 | TRIRIGA-26-12065 | Vandenberg SFB | 77 | Secure Data Facility 77 | Battery Room | 2026-02-05 0745Z | USSPACECOM J2 | Urgent | Structural | 2 | Overhead coiling door not tracking properly; binding intermittently. | Adjust door tracks and lubricate guide system. | Yes – degrades mission operations center readiness. | Submitted | CE Structural
USSPC-FAC-2026-0066 | TRIRIGA-26-12066 | Schriever SFB | 220 | Mission Support Building 220 | Corridor B | 2026-02-05 0800Z | USSPACECOM J6 | Urgent | ESS | 2 | Card reader database sync failure; stale credential data. | Resolve database sync issue and verify credential data. | Yes – supports satellite command and control systems. | Approved | CE ESS
USSPC-FAC-2026-0067 | TRIRIGA-26-12067 | Vandenberg SFB | 51 | Launch Operations Building 51 | Electrical Room | 2026-02-05 0910Z | USSPACECOM J4 | Urgent | Electrical | 3 | Circuit breaker E-6 will not reset after trip; possible internal fault. | Replace faulty circuit breaker and verify proper operation. | Yes – impacts launch operations support systems. | In Progress | CE Electrical
USSPC-FAC-2026-0068 | TRIRIGA-26-12068 | Peterson SFB | 198 | Operations Building 198 | Corridor B | 2026-02-05 1040Z | USSPACECOM J2 | Urgent | HVAC | 2 | Building automation system reporting communication loss with AHU-6 controller. | Restore BAS communication with AHU controller. | Yes – impacts secure communications capability. | Completed | CE HVAC | Inspected system per work order. Identified refrigerant undercharge due to slow leak at service valve. Replaced bearing assembly and balanced fan. Verified airflow and temperature within acceptable parameters. Documentation submitted. | 2026-02-07
USSPC-FAC-2026-0069 | TRIRIGA-26-12069 | Vandenberg SFB | 77 | Secure Data Facility 77 | Loading Dock | 2026-02-05 1045Z | USSPACECOM J6 | Urgent | ESS | 2 | Intercom system non-functional at entry control point. | Repair intercom system and test two-way communication. | Yes – degrades mission operations center readiness. | Approved | CE ESS
USSPC-FAC-2026-0070 | TRIRIGA-26-12070 | Schriever SFB | 400 | Satellite Operations Facility 400 | Antenna Maintenance Area | 2026-02-05 1335Z | USSPACECOM J6 | Preventive Maintenance | ESS | 4 | Preventive maintenance on access control system firmware and hardware. | Perform annual ESS system testing and certification. | No – preventive maintenance. | Scheduled | CE ESS
USSPC-FAC-2026-0071 | TRIRIGA-26-12071 | Peterson SFB | 3 | Power Generation Facility 3 | Generator Bay 2 | 2026-02-05 1600Z | USSPACECOM J3 | Preventive Maintenance | Structural | 4 | Scheduled annual roof inspection and condition assessment. | Perform annual roof condition assessment and document. | No – preventive maintenance. | Completed | CE Structural | Arrived on-site and performed structural assessment. Identified moisture intrusion through failed sealant. Applied membrane patch and verified watertight seal. Condition stable; documented in facility records. | 2026-02-23
USSPC-FAC-2026-0072 | TRIRIGA-26-12072 | Schriever SFB | 302 | Communications Facility 302 | Mechanical Room | 2026-02-05 1745Z | USSPACECOM J3 | Urgent | Electrical | 2 | UPS system reporting degraded battery capacity; estimated runtime below threshold. | Test UPS batteries and replace degraded cells. | Yes – supports satellite uplink equipment. | Completed | CE Electrical | Arrived on-site, performed lockout/tagout, and investigated. Found ATS control board fault. Replaced failed battery cells and load tested string. All circuits tested and verified. Arc flash labels updated. | 2026-02-06
USSPC-FAC-2026-0073 | TRIRIGA-26-12073 | Buckley SFB | 180 | Mission Support Facility 180 | Main Hall | 2026-02-05 2105Z | USSPACECOM J6 | Emergency | HVAC | 1 | Return air temperature sensor reading erratic values; zone control degraded. | Replace return air temperature sensor and recalibrate. | Yes – affects continuous space surveillance mission. | Completed | CE HVAC | Technician responded and found All components inspected and within tolerance. Cleaned coils, replaced filters, lubricated bearings, documented condition. System tested and verified operational at 82°F. All work per UFC 3-410-01. | 2026-02-05
USSPC-FAC-2026-0074 | TRIRIGA-26-12074 | Schriever SFB | 400 | Satellite Operations Facility 400 | Electrical Room | 2026-02-05 2125Z | USSPACECOM J2 | Emergency | HVAC | 2 | Thermostat in zone 7 non-responsive; unable to maintain setpoint. | Replace thermostat and verify zone control operation. | Yes – supports satellite uplink equipment. | Completed | CE HVAC | Arrived on-site, isolated unit, and performed diagnostic. Found seized bearing on supply fan. Cleared drain, treated with biocide, and verified flow. Post-repair monitoring confirmed stable operation. | 2026-02-06
USSPC-FAC-2026-0075 | TRIRIGA-26-12075 | Buckley SFB | 312 | Operations Annex 312 | Secure Entry Vestibule | 2026-02-05 2220Z | USSPACECOM J6 | Urgent | Lighting | 3 | Parking lot light pole 6 dark; ballast or photocell suspected. | Replace ballast or photocell and restore pole light operation. | Yes – affects classified processing environment. | Submitted | CE Lighting
USSPC-FAC-2026-0076 | TRIRIGA-26-12076 | Peterson SFB | 145 | Operations Building 145 | Break Room | 2026-02-05 2345Z | USSPACECOM J6 | Urgent | Structural | 3 | Handrail loose on exterior stairway; anchor bolts corroded. | Secure handrail; replace corroded anchor bolts. | Yes – degrades ground station equipment reliability. | In Progress | CE Structural
USSPC-FAC-2026-0077 | TRIRIGA-26-12077 | Buckley SFB | 312 | Operations Annex 312 | Electrical Room | 2026-02-05 2355Z | USSPACECOM J2 | Routine | Plumbing | 3 | Floor drain backing up intermittently in mechanical room. | Clear floor drain blockage and verify flow. | Yes – affects missile warning operations continuity. | Submitted | CE Plumbing
USSPC-FAC-2026-0078 | TRIRIGA-26-12078 | Peterson SFB | 88 | Data Processing Facility 88 | Server Hall B | 2026-02-06 0135Z | USSPACECOM J2 | Routine | Power Production | 3 | Block heater on standby generator non-functional; engine cold. | Repair or replace block heater and verify engine preheat. | Yes – affects continuous space surveillance mission. | Completed | CE Power Production | Technician inspected generator and support systems. Found block heater element open circuit. Replaced heater element and verified engine block temperature. Generator started, loaded, and verified at rated output. Transfer tested successfully. | 2026-02-24
USSPC-FAC-2026-0079 | TRIRIGA-26-12079 | Peterson SFB | 145 | Operations Building 145 | Conference Room 3 | 2026-02-06 0425Z | USSPACECOM J2 | Urgent | Lighting | 2 | Exit sign lamp out at emergency egress route. | Replace exit sign lamp and verify illumination. | No – preventive maintenance. | In Progress | CE Lighting
USSPC-FAC-2026-0080 | TRIRIGA-26-12080 | Peterson SFB | 3 | Power Generation Facility 3 | Switchgear Room | 2026-02-06 0510Z | USSPACECOM J3 | Emergency | Structural | 2 | Door frame misaligned; secure door not seating properly in frame. | Adjust or replace door frame hardware for proper operation. | Yes – mission-critical data processing environment. | In Progress | CE Structural
USSPC-FAC-2026-0081 | TRIRIGA-26-12081 | Schriever SFB | 400 | Satellite Operations Facility 400 | Equipment Bay | 2026-02-06 0850Z | USSPACECOM J6 | Preventive Maintenance | HVAC | 4 | Server room temperature measured at 92°F due to reduced airflow from AHU-7. | Inspect fan motor bearings and replace if worn. | No – preventive maintenance. | Scheduled | CE HVAC
USSPC-FAC-2026-0082 | TRIRIGA-26-12082 | Schriever SFB | 220 | Mission Support Building 220 | Restroom Wing | 2026-02-06 0930Z | USSPACECOM J3 | Routine | Power Production | 4 | Generator coolant temperature alarm during loaded run test. | Diagnose cooling system alarm and restore normal operation. | No – general facility maintenance. | In Progress | CE Power Production
USSPC-FAC-2026-0083 | TRIRIGA-26-12083 | Peterson SFB | 145 | Operations Building 145 | Restroom Corridor | 2026-02-06 0940Z | USSPACECOM J3 | Routine | Structural | 4 | Raised floor panels loose near network racks. | Secure panels and ensure floor stability. | No – general facility maintenance. | Submitted | CE Structural
USSPC-FAC-2026-0084 | TRIRIGA-26-12084 | Buckley SFB | 180 | Mission Support Facility 180 | Restroom Corridor | 2026-02-06 1110Z | USSPACECOM J2 | Urgent | ESS | 2 | Perimeter fence detection system reporting intermittent faults. | Troubleshoot perimeter detection system and restore monitoring. | No – administrative area; no mission systems affected. | In Progress | CE ESS
USSPC-FAC-2026-0085 | TRIRIGA-26-12085 | Peterson SFB | 105 | Communications Hub 105 | Roof Antenna Platform | 2026-02-06 1410Z | USSPACECOM J2 | Emergency | Structural | 2 | Expansion joint sealant deteriorated on exterior wall; gap visible. | Remove and replace expansion joint sealant. | Yes – degrades mission operations center readiness. | In Progress | CE Structural
USSPC-FAC-2026-0086 | TRIRIGA-26-12086 | Vandenberg SFB | 134 | Range Control Facility 134 | Generator Enclosure | 2026-02-06 1450Z | USSPACECOM J3 | Routine | Lighting | 4 | Lighting control system not responding to occupancy sensors in zone 7. | Troubleshoot occupancy sensor control and restore function. | No – quality of life issue; no mission degradation. | Submitted | CE Lighting
USSPC-FAC-2026-0087 | TRIRIGA-26-12087 | Buckley SFB | 180 | Mission Support Facility 180 | Main Hall | 2026-02-06 1530Z | USSPACECOM J2 | Emergency | Structural | 1 | Handrail loose on exterior stairway; anchor bolts corroded. | Secure handrail; replace corroded anchor bolts. | Yes – supports satellite command and control systems. | In Progress | CE Structural
USSPC-FAC-2026-0088 | TRIRIGA-26-12088 | Schriever SFB | 220 | Mission Support Building 220 | Mechanical Room | 2026-02-06 1625Z | USSPACECOM J4 | Urgent | ESS | 2 | Intrusion detection sensor reporting false alarms in zone 10. | Investigate false alarm source; adjust or replace sensor. | Yes – degrades ground station equipment reliability. | In Progress | CE ESS
USSPC-FAC-2026-0089 | TRIRIGA-26-12089 | Vandenberg SFB | 134 | Range Control Facility 134 | Exterior HVAC Pad | 2026-02-06 1720Z | USSPACECOM J6 | Routine | HVAC | 3 | Ductwork insulation degraded in mechanical chase; condensation dripping onto ceiling tiles. | Replace degraded duct insulation and remediate moisture. | Yes – impacts launch operations support systems. | Completed | CE HVAC | Technician responded and found Identified failed compressor contactor. Cleaned coils, replaced filters, lubricated bearings, documented condition. System tested and verified operational at 81°F. All work per UFC 3-410-01. | 2026-02-09
USSPC-FAC-2026-0090 | TRIRIGA-26-12090 | Schriever SFB | 302 | Communications Facility 302 | Equipment Room 2 | 2026-02-06 1725Z | USSPACECOM J3 | Preventive Maintenance | HVAC | 4 | Seasonal changeover inspection required for heating/cooling systems. | Perform seasonal changeover inspection and adjustments. | No – preventive maintenance. | Scheduled | CE HVAC
USSPC-FAC-2026-0091 | TRIRIGA-26-12091 | Vandenberg SFB | 51 | Launch Operations Building 51 | Electrical Room | 2026-02-06 1810Z | USSPACECOM J3 | Routine | HVAC | 4 | Cooling unit shut down unexpectedly; room temperature rising steadily. | Restore HVAC operation and verify system stability. | No – personnel safety and usability concern. | Submitted | CE HVAC
USSPC-FAC-2026-0092 | TRIRIGA-26-12092 | Schriever SFB | 155 | Operations Building 155 | Comm Closet 3A | 2026-02-06 1820Z | USSPACECOM J2 | Routine | Fire Protection | 4 | Fire rated wall penetration unsealed in mechanical room. | Seal fire-rated wall penetration with listed firestop material. | Potential – degradation may affect future mission readiness. | Completed | CE Fire Protection | Technician inspected system per NFPA 72/25 requirements. Identified leaking sprinkler system check valve. Recharged agent bottles to rated pressure. System placed back in service and tested. All zones normal. | 2026-02-20
USSPC-FAC-2026-0093 | TRIRIGA-26-12093 | Peterson SFB | 88 | Data Processing Facility 88 | Server Hall A | 2026-02-06 1845Z | USSPACECOM J3 | Routine | Fire Protection | 3 | Sprinkler system pressure gauge reading below minimum; 30 PSI observed. | Investigate low sprinkler pressure and restore to minimum. | Yes – degrades mission operations center readiness. | Completed | CE Fire Protection | Technician inspected system per NFPA 72/25 requirements. Identified low agent bottle pressure from slow leak. Replaced detector head and tested with canned smoke. System placed back in service and tested. All zones normal. | 2026-02-13
USSPC-FAC-2026-0094 | TRIRIGA-26-12094 | Buckley SFB | 312 | Operations Annex 312 | Electrical Room | 2026-02-06 1925Z | USSPACECOM J6 | Routine | Lighting | 3 | Emergency lighting battery unit failed self-test; no backup illumination. | Replace emergency lighting battery unit and test. | No – administrative area; no mission systems affected. | Approved | CE Lighting
USSPC-FAC-2026-0095 | TRIRIGA-26-12095 | Buckley SFB | 312 | Operations Annex 312 | Secure Entry Vestibule | 2026-02-06 1945Z | USSPACECOM J6 | Preventive Maintenance | ESS | 4 | Preventive maintenance on access control system firmware and hardware. | Inspect access control hardware and repair or replace reader. | No – preventive maintenance. | Approved | CE ESS
USSPC-FAC-2026-0096 | TRIRIGA-26-12096 | Peterson SFB | 42 | Administrative Building 42 | Roof Access | 2026-02-06 1950Z | USSPACECOM J2 | Emergency | ESS | 2 | Card reader database sync failure; stale credential data. | Resolve database sync issue and verify credential data. | Yes – supports satellite command and control systems. | Approved | CE ESS
USSPC-FAC-2026-0097 | TRIRIGA-26-12097 | Peterson SFB | 88 | Data Processing Facility 88 | Receiving Area | 2026-02-06 2050Z | USSPACECOM J6 | Emergency | ESS | 2 | Motion sensor PIR detector degraded; detection range reduced. | Replace PIR motion sensor and verify detection coverage. | Yes – affects missile warning operations continuity. | Approved | CE ESS
USSPC-FAC-2026-0098 | TRIRIGA-26-12098 | Peterson SFB | 145 | Operations Building 145 | Entry Vestibule | 2026-02-06 2140Z | USSPACECOM J3 | Routine | ESS | 3 | Intrusion detection sensor reporting false alarms in zone 2. | Investigate false alarm source; adjust or replace sensor. | Yes – degrades mission operations center readiness. | Completed | CE ESS | Responded and coordinated with security forces. Found failed card reader magnetic head. Replaced lock solenoid and tested with valid credentials. Credentials tested at affected entry points; full functionality confirmed. | 2026-02-10
USSPC-FAC-2026-0099 | TRIRIGA-26-12099 | Schriever SFB | 302 | Communications Facility 302 | Roof | 2026-02-06 2200Z | USSPACECOM J2 | Routine | Lighting | 4 | Exit sign lamp out at emergency egress route. | Replace exit sign lamp and verify illumination. | No – aesthetic/comfort issue only. | In Progress | CE Lighting
USSPC-FAC-2026-0100 | TRIRIGA-26-12100 | Peterson SFB | 88 | Data Processing Facility 88 | Electrical Vault | 2026-02-06 2245Z | USSPACECOM J4 | Routine | Plumbing | 4 | Isolation valve on chilled water loop will not fully close; stem corroded. | Replace isolation valve and verify system integrity. | No – administrative area; no mission systems affected. | Submitted | CE Plumbing
USSPC-FAC-2026-0101 | TRIRIGA-26-12101 | Peterson SFB | 88 | Data Processing Facility 88 | Receiving Area | 2026-02-07 0055Z | USSPACECOM J6 | Urgent | HVAC | 2 | Server room temperature measured at 88°F due to reduced airflow from AHU-1. | Inspect and repair air handling unit; restore cooling to acceptable range. | Yes – delayed access to mission operations spaces. | In Progress | CE HVAC
USSPC-FAC-2026-0102 | TRIRIGA-26-12102 | Peterson SFB | 88 | Data Processing Facility 88 | Battery Room | 2026-02-07 0155Z | USSPACECOM J6 | Urgent | Plumbing | 3 | Water hammer occurring in supply piping when fixtures cycle. | Install water hammer arrestors and secure piping supports. | Potential – degradation may affect future mission readiness. | Approved | CE Plumbing
USSPC-FAC-2026-0103 | TRIRIGA-26-12103 | Peterson SFB | 145 | Operations Building 145 | Restroom Corridor | 2026-02-07 0345Z | USSPACECOM J4 | Urgent | Structural | 3 | Crack observed in exterior wall exceeding 1/4 inch width; moisture intrusion suspected. | Assess crack, seal exterior, and monitor for propagation. | No – general facility maintenance. | Approved | CE Structural
USSPC-FAC-2026-0104 | TRIRIGA-26-12104 | Schriever SFB | 400 | Satellite Operations Facility 400 | Antenna Maintenance Area | 2026-02-07 0435Z | USSPACECOM J6 | Preventive Maintenance | Plumbing | 4 | Preventive maintenance on domestic water heaters per annual schedule. | Inspect and repair T&P relief valve; verify operation. | No – preventive maintenance. | Scheduled | CE Plumbing
USSPC-FAC-2026-0105 | TRIRIGA-26-12105 | Vandenberg SFB | 77 | Secure Data Facility 77 | Server Room B | 2026-02-07 0440Z | USSPACECOM J3 | Emergency | Lighting | 1 | LED retrofit fixture failed prematurely; driver humming audible. | Replace failed LED driver and fixture. | Yes – intermittent loss of operator consoles. | In Progress | CE Lighting
USSPC-FAC-2026-0106 | TRIRIGA-26-12106 | Schriever SFB | 220 | Mission Support Building 220 | Electrical Closet | 2026-02-07 0525Z | USSPACECOM J4 | Urgent | Electrical | 2 | Power monitoring system reporting harmonics above threshold on critical bus. | Install harmonic filtering or identify harmonic source. | Yes – intermittent loss of operator consoles. | Completed | CE Electrical | Technician de-energized and inspected per NFPA 70E. Identified overloaded circuit from unauthorized load addition. Replaced damaged conductor section and resealed conduit. System re-energized and tested under load; operating normally. | 2026-02-08
USSPC-FAC-2026-0107 | TRIRIGA-26-12107 | Schriever SFB | 220 | Mission Support Building 220 | Mechanical Room | 2026-02-07 0535Z | USSPACECOM J2 | Emergency | Lighting | 1 | Flickering fluorescent fixtures in office area causing occupant complaints. | Replace flickering fixtures with new lamps or ballasts. | Yes – intermittent loss of operator consoles. | Approved | CE Lighting
USSPC-FAC-2026-0108 | TRIRIGA-26-12108 | Schriever SFB | 302 | Communications Facility 302 | Cable Tray Area | 2026-02-07 0605Z | USSPACECOM J6 | Urgent | Fire Protection | 2 | Fire pump failed to start during weekly test sequence. | Troubleshoot fire pump controller and restore start capability. | Yes – impacts secure communications capability. | Approved | CE Fire Protection
USSPC-FAC-2026-0109 | TRIRIGA-26-12109 | Vandenberg SFB | 134 | Range Control Facility 134 | Telemetry Room | 2026-02-07 0635Z | USSPACECOM J4 | Emergency | Plumbing | 1 | Floor drain backing up intermittently in mechanical room. | Clear floor drain blockage and verify flow. | Yes – supports satellite command and control systems. | Completed | CE Plumbing | Technician inspected and identified Found corroded pipe fitting at joint. Cut out corroded fitting and installed new coupling. System pressure tested and verified at normal operating range. No further leaks observed. | 2026-02-09
USSPC-FAC-2026-0110 | TRIRIGA-26-12110 | Peterson SFB | 105 | Communications Hub 105 | Antenna Equipment Room | 2026-02-07 0715Z | USSPACECOM J4 | Preventive Maintenance | Plumbing | 4 | Backflow preventer failed annual test; requires rebuild or replacement. | Perform backflow preventer testing and submit certification. | No – preventive maintenance. | In Progress | CE Plumbing
USSPC-FAC-2026-0111 | TRIRIGA-26-12111 | Vandenberg SFB | 77 | Secure Data Facility 77 | Battery Room | 2026-02-07 0815Z | USSPACECOM J4 | Emergency | ESS | 2 | Electronic lock on secure door not responding to valid credentials. | Replace electronic lock actuator and verify operation. | Yes – impacts launch operations support systems. | In Progress | CE ESS
USSPC-FAC-2026-0112 | TRIRIGA-26-12112 | Buckley SFB | 312 | Operations Annex 312 | Rooftop | 2026-02-07 0835Z | USSPACECOM J3 | Urgent | Structural | 2 | Roof membrane damage identified during routine walk-down; ponding water present. | Repair roof membrane and address ponding condition. | No – personnel safety concern. | Approved | CE Structural
USSPC-FAC-2026-0113 | TRIRIGA-26-12113 | Schriever SFB | 302 | Communications Facility 302 | Mechanical Room | 2026-02-07 0955Z | USSPACECOM J4 | Routine | Lighting | 3 | Parking lot light pole 3 dark; ballast or photocell suspected. | Replace ballast or photocell and restore pole light operation. | Yes – mission-critical data processing environment. | Submitted | CE Lighting
USSPC-FAC-2026-0114 | TRIRIGA-26-12114 | Peterson SFB | 105 | Communications Hub 105 | Ground Floor Lobby | 2026-02-07 1035Z | USSPACECOM J4 | Urgent | ESS | 2 | Card reader database sync failure; stale credential data. | Resolve database sync issue and verify credential data. | Yes – degrades mission operations center readiness. | Completed | CE ESS | Responded and coordinated with security forces. Found door lock solenoid failure. Updated firmware and re-established communication. Credentials tested at affected entry points; full functionality confirmed. | 2026-02-08
USSPC-FAC-2026-0115 | TRIRIGA-26-12115 | Buckley SFB | 180 | Mission Support Facility 180 | Equipment Room A | 2026-02-07 1155Z | USSPACECOM J2 | Routine | HVAC | 3 | Intermittent fault on CRAC unit 1; temperature cycling outside acceptable range. | Troubleshoot CRAC unit fault and restore environmental controls. | No – preventive maintenance. | Approved | CE HVAC
USSPC-FAC-2026-0116 | TRIRIGA-26-12116 | Peterson SFB | 88 | Data Processing Facility 88 | Electrical Vault | 2026-02-07 1450Z | USSPACECOM J6 | Urgent | Fire Protection | 2 | Clean agent suppression system showing low bottle pressure. | Recharge or replace clean agent suppression bottles. | Yes – supports satellite uplink equipment. | In Progress | CE Fire Protection
USSPC-FAC-2026-0117 | TRIRIGA-26-12117 | Schriever SFB | 400 | Satellite Operations Facility 400 | Ground Station Control Room | 2026-02-07 1850Z | USSPACECOM J4 | Urgent | Power Production | 2 | Automatic transfer switch not sensing utility power loss correctly. | Troubleshoot ATS sensing circuit and restore proper operation. | Yes – supports space domain awareness operations. | In Progress | CE Power Production
USSPC-FAC-2026-0118 | TRIRIGA-26-12118 | Schriever SFB | 220 | Mission Support Building 220 | Mechanical Room | 2026-02-07 1910Z | USSPACECOM J3 | Urgent | Lighting | 3 | Lighting control system not responding to occupancy sensors in zone 1. | Troubleshoot occupancy sensor control and restore function. | No – quality of life issue; no mission degradation. | Completed | CE Lighting | Arrived on-site and assessed lighting condition. Discovered failed photocell. Replaced ballast and installed new lamps. Area lighting restored to full operation. | 2026-02-08
USSPC-FAC-2026-0119 | TRIRIGA-26-12119 | Vandenberg SFB | 77 | Secure Data Facility 77 | Loading Dock | 2026-02-07 1940Z | USSPACECOM J3 | Urgent | Plumbing | 3 | Water heater temperature/pressure relief valve discharging intermittently. | Inspect and repair T&P relief valve; verify operation. | Yes – impacts real-time telemetry processing. | In Progress | CE Plumbing
USSPC-FAC-2026-0120 | TRIRIGA-26-12120 | Peterson SFB | 105 | Communications Hub 105 | Cable Vault | 2026-02-07 2020Z | USSPACECOM J2 | Preventive Maintenance | Structural | 4 | Scheduled annual roof inspection and condition assessment. | Service overhead doors and dock leveler mechanisms. | No – preventive maintenance. | Completed | CE Structural | Arrived on-site and performed structural assessment. Found deteriorated roof membrane at flashing detail. Patched spalled area with structural repair mortar. Condition stable; documented in facility records. | 2026-02-27
USSPC-FAC-2026-0121 | TRIRIGA-26-12121 | Buckley SFB | 180 | Mission Support Facility 180 | Equipment Room A | 2026-02-07 2200Z | USSPACECOM J4 | Urgent | Structural | 2 | Window seal failure; condensation forming between panes. | Replace failed window seal unit. | Yes – impacts real-time telemetry processing. | In Progress | CE Structural
USSPC-FAC-2026-0122 | TRIRIGA-26-12122 | Schriever SFB | 220 | Mission Support Building 220 | Mechanical Room | 2026-02-07 2230Z | USSPACECOM J6 | Routine | Fire Protection | 4 | Fire rated wall penetration unsealed in mechanical room. | Seal fire-rated wall penetration with listed firestop material. | No – preventive maintenance. | Approved | CE Fire Protection
USSPC-FAC-2026-0123 | TRIRIGA-26-12123 | Schriever SFB | 220 | Mission Support Building 220 | Mechanical Room | 2026-02-08 0050Z | USSPACECOM J4 | Urgent | HVAC | 2 | Building automation system reporting communication loss with AHU-7 controller. | Restore BAS communication with AHU controller. | No – general facility maintenance. | Completed | CE HVAC | Technician responded and found Found failed capacitor on compressor. Replaced communication card and restored BAS integration. System tested and verified operational at 84°F. All work per UFC 3-410-01. | 2026-02-10
USSPC-FAC-2026-0124 | TRIRIGA-26-12124 | Vandenberg SFB | 134 | Range Control Facility 134 | Telemetry Room | 2026-02-08 0135Z | USSPACECOM J2 | Emergency | HVAC | 2 | Cooling unit shut down unexpectedly; room temperature rising steadily. | Restore HVAC operation and verify system stability. | Yes – affects missile warning operations continuity. | In Progress | CE HVAC
USSPC-FAC-2026-0125 | TRIRIGA-26-12125 | Schriever SFB | 220 | Mission Support Building 220 | Training Room | 2026-02-08 0305Z | USSPACECOM J3 | Urgent | Fire Protection | 3 | Emergency exit sign non-illuminated in corridor section. | Replace emergency exit sign lamps and verify illumination. | Yes – degrades ground station equipment reliability. | Approved | CE Fire Protection
USSPC-FAC-2026-0126 | TRIRIGA-26-12126 | Schriever SFB | 155 | Operations Building 155 | Electrical Room 2 | 2026-02-08 0510Z | USSPACECOM J6 | Routine | Fire Protection | 4 | Emergency exit sign non-illuminated in corridor section. | Replace emergency exit sign lamps and verify illumination. | No – aesthetic/comfort issue only. | Completed | CE Fire Protection | Responded and placed system in test mode. Discovered failed fire alarm control module. Replaced pull station and tested alarm signal to panel. Fire alarm panel cleared; all devices verified operational. | 2026-02-22
USSPC-FAC-2026-0127 | TRIRIGA-26-12127 | Peterson SFB | 198 | Operations Building 198 | Electrical Room | 2026-02-08 0515Z | USSPACECOM J6 | Emergency | Plumbing | 1 | Minor water leak observed on chilled water return line. | Repair leaking pipe section and verify system pressure. | Yes – degrades mission operations center readiness. | In Progress | CE Plumbing
USSPC-FAC-2026-0128 | TRIRIGA-26-12128 | Vandenberg SFB | 51 | Launch Operations Building 51 | Roof | 2026-02-08 0605Z | USSPACECOM J6 | Urgent | HVAC | 2 | Thermostat in zone 5 non-responsive; unable to maintain setpoint. | Replace thermostat and verify zone control operation. | Yes – affects continuous space surveillance mission. | Approved | CE HVAC
USSPC-FAC-2026-0129 | TRIRIGA-26-12129 | Vandenberg SFB | 77 | Secure Data Facility 77 | Server Room A | 2026-02-08 0625Z | USSPACECOM J6 | Routine | Plumbing | 4 | Restroom fixture running continuously; float valve suspected faulty. | Replace fixture valve components and verify operation. | No – aesthetic/comfort issue only. | In Progress | CE Plumbing
USSPC-FAC-2026-0130 | TRIRIGA-26-12130 | Peterson SFB | 105 | Communications Hub 105 | Cable Vault | 2026-02-08 0850Z | USSPACECOM J4 | Preventive Maintenance | Lighting | 4 | Scheduled annual emergency lighting 90-minute battery test. | Replace emergency lighting battery unit and test. | No – preventive maintenance. | Scheduled | CE Lighting
USSPC-FAC-2026-0131 | TRIRIGA-26-12131 | Buckley SFB | 180 | Mission Support Facility 180 | Equipment Room A | 2026-02-08 1045Z | USSPACECOM J4 | Urgent | Electrical | 2 | Phase imbalance measured at 5% on main distribution panel. | Balance phase loading on main distribution panel. | Potential – degradation may affect future mission readiness. | Submitted | CE Electrical
USSPC-FAC-2026-0132 | TRIRIGA-26-12132 | Schriever SFB | 220 | Mission Support Building 220 | Lobby | 2026-02-08 1055Z | USSPACECOM J6 | Routine | Electrical | 3 | Power monitoring system reporting harmonics above threshold on critical bus. | Install harmonic filtering or identify harmonic source. | Yes – supports satellite command and control systems. | In Progress | CE Electrical
USSPC-FAC-2026-0133 | TRIRIGA-26-12133 | Vandenberg SFB | 51 | Launch Operations Building 51 | Roof | 2026-02-08 1335Z | USSPACECOM J4 | Routine | ESS | 4 | Perimeter fence detection system reporting intermittent faults. | Troubleshoot perimeter detection system and restore monitoring. | Potential – could impact mission systems if leak reaches equipment. | In Progress | CE ESS
USSPC-FAC-2026-0134 | TRIRIGA-26-12134 | Peterson SFB | 88 | Data Processing Facility 88 | Server Hall B | 2026-02-08 1600Z | USSPACECOM J2 | Urgent | HVAC | 3 | Variable frequency drive on AHU-6 faulting intermittently under load. | Troubleshoot VFD fault and restore fan operation. | Potential – potential cascade failure if not addressed. | In Progress | CE HVAC
USSPC-FAC-2026-0135 | TRIRIGA-26-12135 | Peterson SFB | 198 | Operations Building 198 | Corridor A | 2026-02-08 1735Z | USSPACECOM J4 | Routine | Electrical | 4 | Intermittent power loss to operator consoles on ops floor. | Troubleshoot intermittent power issue and restore stable supply. | No – preventive maintenance. | Submitted | CE Electrical
USSPC-FAC-2026-0136 | TRIRIGA-26-12136 | Peterson SFB | 210 | Operations Building 210 | Mechanical Penthouse | 2026-02-09 0055Z | USSPACECOM J2 | Emergency | Structural | 2 | Door frame misaligned; secure door not seating properly in frame. | Adjust or replace door frame hardware for proper operation. | Yes – delayed access to mission operations spaces. | Completed | CE Structural | Technician assessed condition and documented findings. Identified moisture intrusion through failed sealant. Applied new sealant and verified weathertight condition. Area safe for occupancy. Follow-up inspection scheduled if required. | 2026-02-10
USSPC-FAC-2026-0137 | TRIRIGA-26-12137 | Peterson SFB | 105 | Communications Hub 105 | Cable Vault | 2026-02-09 0145Z | USSPACECOM J4 | Routine | HVAC | 3 | Ductwork insulation degraded in mechanical chase; condensation dripping onto ceiling tiles. | Replace degraded duct insulation and remediate moisture. | Yes – affects missile warning operations continuity. | Submitted | CE HVAC
USSPC-FAC-2026-0138 | TRIRIGA-26-12138 | Peterson SFB | 145 | Operations Building 145 | Ops Floor | 2026-02-09 0605Z | USSPACECOM J3 | Urgent | Plumbing | 3 | Corrosion visible on exposed copper piping in mechanical chase. | Evaluate pipe corrosion and replace affected sections. | No – aesthetic/comfort issue only. | In Progress | CE Plumbing
USSPC-FAC-2026-0139 | TRIRIGA-26-12139 | Schriever SFB | 155 | Operations Building 155 | Comm Closet 3A | 2026-02-09 0740Z | USSPACECOM J2 | Preventive Maintenance | Lighting | 4 | Preventive maintenance on exterior lighting and photocell replacement. | Inspect and replace photocells on exterior fixtures. | No – preventive maintenance. | Completed | CE Lighting | Technician inspected lighting system. Found failed LED driver. Repaired wiring connection and verified circuit integrity. All fixtures verified operational; light levels measured and within IES standards. | 2026-02-25
USSPC-FAC-2026-0140 | TRIRIGA-26-12140 | Peterson SFB | 88 | Data Processing Facility 88 | Mechanical Room | 2026-02-09 0845Z | USSPACECOM J4 | Emergency | Structural | 1 | Overhead coiling door not tracking properly; binding intermittently. | Adjust door tracks and lubricate guide system. | Yes – impacts secure communications capability. | In Progress | CE Structural
USSPC-FAC-2026-0141 | TRIRIGA-26-12141 | Peterson SFB | 42 | Administrative Building 42 | Records Room | 2026-02-09 0855Z | USSPACECOM J3 | Routine | ESS | 3 | Duress alarm button at post 2 non-functional during test. | Replace duress alarm switch and test signaling. | Yes – loss of backup power to mission facilities. | Approved | CE ESS
USSPC-FAC-2026-0142 | TRIRIGA-26-12142 | Buckley SFB | 312 | Operations Annex 312 | Mechanical Room | 2026-02-09 0945Z | USSPACECOM J3 | Preventive Maintenance | ESS | 4 | Preventive maintenance on access control system firmware and hardware. | Inspect access control hardware and repair or replace reader. | No – preventive maintenance. | Completed | CE ESS | Responded and coordinated with security forces. Discovered PIR sensor lens contamination. Updated firmware and re-established communication. Credentials tested at affected entry points; full functionality confirmed. | 2026-02-24
USSPC-FAC-2026-0143 | TRIRIGA-26-12143 | Schriever SFB | 400 | Satellite Operations Facility 400 | Antenna Maintenance Area | 2026-02-09 1040Z | USSPACECOM J4 | Urgent | Fire Protection | 2 | Sprinkler system pressure gauge reading below minimum; 37 PSI observed. | Investigate low sprinkler pressure and restore to minimum. | No – preventive maintenance. | Approved | CE Fire Protection
USSPC-FAC-2026-0144 | TRIRIGA-26-12144 | Schriever SFB | 220 | Mission Support Building 220 | Restroom Wing | 2026-02-09 1405Z | USSPACECOM J2 | Routine | Fire Protection | 3 | Sprinkler head obstructed by stored materials in equipment room. | Clear obstructions from sprinkler head coverage area. | Yes – loss of backup power to mission facilities. | Approved | CE Fire Protection
USSPC-FAC-2026-0145 | TRIRIGA-26-12145 | Peterson SFB | 3 | Power Generation Facility 3 | Transfer Switch Room | 2026-02-09 1435Z | USSPACECOM J4 | Routine | HVAC | 4 | Refrigerant leak suspected on split system unit; ice formation on suction line. | Locate and repair refrigerant leak; recharge system to spec. | No – preventive maintenance. | Submitted | CE HVAC
USSPC-FAC-2026-0146 | TRIRIGA-26-12146 | Peterson SFB | 198 | Operations Building 198 | Lobby | 2026-02-09 1810Z | USSPACECOM J6 | Urgent | ESS | 2 | Perimeter fence detection system reporting intermittent faults. | Troubleshoot perimeter detection system and restore monitoring. | Potential – could impact mission systems if leak reaches equipment. | Completed | CE ESS | Technician inspected ESS components. Identified controller firmware communication error. Replaced network cable and verified video feed. System tested end-to-end; all access points verified operational. Security notified of restoration. | 2026-02-13
USSPC-FAC-2026-0147 | TRIRIGA-26-12147 | Schriever SFB | 400 | Satellite Operations Facility 400 | Antenna Maintenance Area | 2026-02-09 1935Z | USSPACECOM J2 | Emergency | Fire Protection | 2 | Fire door held open with unauthorized wedge; closer mechanism degraded. | Repair fire door closer mechanism and verify self-closing. | Yes – affects classified processing environment. | Approved | CE Fire Protection
USSPC-FAC-2026-0148 | TRIRIGA-26-12148 | Vandenberg SFB | 77 | Secure Data Facility 77 | Server Room B | 2026-02-09 1945Z | USSPACECOM J2 | Routine | Plumbing | 4 | Water heater temperature/pressure relief valve discharging intermittently. | Inspect and repair T&P relief valve; verify operation. | No – routine upkeep; no operational impact. | Approved | CE Plumbing
USSPC-FAC-2026-0149 | TRIRIGA-26-12149 | Peterson SFB | 42 | Administrative Building 42 | Restroom A | 2026-02-09 2050Z | USSPACECOM J4 | Urgent | ESS | 2 | Motion sensor PIR detector degraded; detection range reduced. | Replace PIR motion sensor and verify detection coverage. | Yes – degrades mission operations center readiness. | Approved | CE ESS
USSPC-FAC-2026-0150 | TRIRIGA-26-12150 | Schriever SFB | 220 | Mission Support Building 220 | Corridor B | 2026-02-09 2220Z | USSPACECOM J3 | Emergency | Plumbing | 2 | Floor drain backing up intermittently in mechanical room. | Clear floor drain blockage and verify flow. | Yes – supports satellite uplink equipment. | Approved | CE Plumbing
USSPC-FAC-2026-0151 | TRIRIGA-26-12151 | Schriever SFB | 220 | Mission Support Building 220 | Mechanical Room | 2026-02-09 2255Z | USSPACECOM J3 | Emergency | Fire Protection | 2 | Fire rated wall penetration unsealed in mechanical room. | Seal fire-rated wall penetration with listed firestop material. | Yes – degrades mission operations center readiness. | In Progress | CE Fire Protection
USSPC-FAC-2026-0152 | TRIRIGA-26-12152 | Peterson SFB | 145 | Operations Building 145 | Entry Vestibule | 2026-02-09 2355Z | USSPACECOM J2 | Urgent | Electrical | 2 | Frequent breaker trips observed on mission operations power panel E-11. | Inspect panel, identify overload condition, and replace faulty breakers. | No – quality of life issue; no mission degradation. | Approved | CE Electrical
USSPC-FAC-2026-0153 | TRIRIGA-26-12153 | Buckley SFB | 180 | Mission Support Facility 180 | Restroom Corridor | 2026-02-10 0000Z | USSPACECOM J6 | Routine | Structural | 4 | Ceiling tile damage from water intrusion; multiple tiles sagging. | Replace damaged ceiling tiles and identify water source. | No – administrative area; no mission systems affected. | In Progress | CE Structural
USSPC-FAC-2026-0154 | TRIRIGA-26-12154 | Schriever SFB | 400 | Satellite Operations Facility 400 | Server Room | 2026-02-10 0240Z | USSPACECOM J3 | Urgent | Power Production | 3 | Fuel quality test results indicate water contamination in storage tank. | Drain contaminated fuel, polish tank, and resample. | Yes – supports satellite command and control systems. | Completed | CE Power Production | Technician inspected generator and support systems. Found low coolant level from radiator seep. Replaced charger rectifier and verified float/equalize modes. Generator started, loaded, and verified at rated output. Transfer tested successfully. | 2026-02-14
USSPC-FAC-2026-0155 | TRIRIGA-26-12155 | Buckley SFB | 180 | Mission Support Facility 180 | Mechanical Room | 2026-02-10 0415Z | USSPACECOM J2 | Emergency | Plumbing | 2 | Minor water leak observed on chilled water return line. | Repair leaking pipe section and verify system pressure. | Yes – impacts secure communications capability. | Completed | CE Plumbing | Technician inspected and identified Found internal disc failure in backflow preventer. Replaced mixing valve and set to 120°F output. System pressure tested and verified at normal operating range. No further leaks observed. | 2026-02-10
USSPC-FAC-2026-0156 | TRIRIGA-26-12156 | Vandenberg SFB | 51 | Launch Operations Building 51 | Control Room | 2026-02-10 1000Z | USSPACECOM J3 | Urgent | HVAC | 3 | Chilled water supply temperature elevated; cooling capacity reduced by approximately 30%. | Diagnose chilled water temperature issue and restore capacity. | Yes – delayed access to mission operations spaces. | Approved | CE HVAC
USSPC-FAC-2026-0157 | TRIRIGA-26-12157 | Schriever SFB | 220 | Mission Support Building 220 | Restroom Wing | 2026-02-10 1045Z | USSPACECOM J4 | Urgent | Lighting | 2 | Emergency lighting battery unit failed self-test; no backup illumination. | Replace emergency lighting battery unit and test. | Potential – could impact mission systems if leak reaches equipment. | Approved | CE Lighting
USSPC-FAC-2026-0158 | TRIRIGA-26-12158 | Peterson SFB | 210 | Operations Building 210 | Electrical Room 1A | 2026-02-10 1335Z | USSPACECOM J4 | Urgent | Structural | 3 | Door frame misaligned; secure door not seating properly in frame. | Adjust or replace door frame hardware for proper operation. | No – general facility maintenance. | Submitted | CE Structural
USSPC-FAC-2026-0159 | TRIRIGA-26-12159 | Vandenberg SFB | 77 | Secure Data Facility 77 | Mechanical Room | 2026-02-10 1430Z | USSPACECOM J6 | Routine | ESS | 4 | Motion sensor PIR detector degraded; detection range reduced. | Replace PIR motion sensor and verify detection coverage. | Potential – potential cascade failure if not addressed. | Approved | CE ESS
USSPC-FAC-2026-0160 | TRIRIGA-26-12160 | Buckley SFB | 312 | Operations Annex 312 | Rooftop | 2026-02-10 1805Z | USSPACECOM J6 | Emergency | Structural | 2 | Concrete spalling on loading dock surface; rebar partially exposed. | Patch spalled concrete and apply protective coating. | Yes – intermittent loss of operator consoles. | Completed | CE Structural | Technician assessed condition and documented findings. Discovered freeze-thaw damage to concrete surface. Applied new sealant and verified weathertight condition. Area safe for occupancy. Follow-up inspection scheduled if required. | 2026-02-12
USSPC-FAC-2026-0161 | TRIRIGA-26-12161 | Vandenberg SFB | 77 | Secure Data Facility 77 | Mechanical Room | 2026-02-10 1910Z | USSPACECOM J2 | Urgent | Electrical | 3 | PDU in server room reporting overload alarm on Phase B. | Investigate PDU overload and redistribute loads as needed. | No – preventive maintenance. | In Progress | CE Electrical
USSPC-FAC-2026-0162 | TRIRIGA-26-12162 | Vandenberg SFB | 134 | Range Control Facility 134 | Generator Enclosure | 2026-02-10 1945Z | USSPACECOM J6 | Emergency | Power Production | 1 | Generator load bank test revealed 14% capacity degradation. | Investigate capacity loss and perform corrective maintenance. | Yes – degrades mission operations center readiness. | Completed | CE Power Production | Technician inspected generator and support systems. Identified voltage regulator out of calibration. Recalibrated voltage regulator and verified output under load. Generator started, loaded, and verified at rated output. Transfer tested successfully. | 2026-02-11
USSPC-FAC-2026-0163 | TRIRIGA-26-12163 | Schriever SFB | 400 | Satellite Operations Facility 400 | Equipment Bay | 2026-02-10 2040Z | USSPACECOM J2 | Routine | Power Production | 4 | Block heater on standby generator non-functional; engine cold. | Repair or replace block heater and verify engine preheat. | Potential – risk to nearby equipment if condition worsens. | Submitted | CE Power Production
USSPC-FAC-2026-0164 | TRIRIGA-26-12164 | Vandenberg SFB | 77 | Secure Data Facility 77 | Loading Dock | 2026-02-10 2105Z | USSPACECOM J2 | Preventive Maintenance | HVAC | 4 | Rooftop unit 2 failed to start during scheduled cycle; compressor locked out. | Inspect, clean, and document AHU condition. | No – preventive maintenance. | In Progress | CE HVAC
USSPC-FAC-2026-0165 | TRIRIGA-26-12165 | Buckley SFB | 312 | Operations Annex 312 | Rooftop | 2026-02-10 2210Z | USSPACECOM J2 | Emergency | Power Production | 2 | Generator exhaust leak detected at flexible coupling. | Repair exhaust leak and verify emissions containment. | Yes – loss of backup power to mission facilities. | Completed | CE Power Production | Responded and performed diagnostic on power production equipment. Found failed starter motor solenoid. Replaced check valve and tested fuel transfer operation. Full load test passed; auto-start verified. Logbook updated. | 2026-02-11
USSPC-FAC-2026-0166 | TRIRIGA-26-12166 | Peterson SFB | 3 | Power Generation Facility 3 | Switchgear Room | 2026-02-10 2255Z | USSPACECOM J6 | Emergency | Plumbing | 2 | Isolation valve on chilled water loop will not fully close; stem corroded. | Replace isolation valve and verify system integrity. | Yes – intermittent loss of operator consoles. | In Progress | CE Plumbing
USSPC-FAC-2026-0167 | TRIRIGA-26-12167 | Vandenberg SFB | 77 | Secure Data Facility 77 | Server Room B | 2026-02-10 2335Z | USSPACECOM J4 | Emergency | Power Production | 2 | Fuel transfer pump inoperative; unable to refill day tank. | Repair or replace fuel transfer pump. | Yes – degrades ground station equipment reliability. | Approved | CE Power Production
USSPC-FAC-2026-0168 | TRIRIGA-26-12168 | Vandenberg SFB | 77 | Secure Data Facility 77 | Battery Room | 2026-02-11 0005Z | USSPACECOM J3 | Preventive Maintenance | ESS | 4 | Preventive maintenance on access control system firmware and hardware. | Replace duress alarm switch and test signaling. | No – preventive maintenance. | Approved | CE ESS
USSPC-FAC-2026-0169 | TRIRIGA-26-12169 | Schriever SFB | 155 | Operations Building 155 | Watch Floor | 2026-02-11 0145Z | USSPACECOM J2 | Preventive Maintenance | Plumbing | 4 | Preventive maintenance on domestic water heaters per annual schedule. | Service water heaters per annual maintenance plan. | No – preventive maintenance. | Scheduled | CE Plumbing
USSPC-FAC-2026-0170 | TRIRIGA-26-12170 | Peterson SFB | 198 | Operations Building 198 | Electrical Room | 2026-02-11 0200Z | USSPACECOM J4 | Routine | Plumbing | 4 | Restroom fixture running continuously; float valve suspected faulty. | Replace fixture valve components and verify operation. | No – preventive maintenance. | In Progress | CE Plumbing
USSPC-FAC-2026-0171 | TRIRIGA-26-12171 | Vandenberg SFB | 51 | Launch Operations Building 51 | Mechanical Room | 2026-02-11 0220Z | USSPACECOM J4 | Routine | HVAC | 3 | Exhaust fan inoperative in mechanical room; ambient temperature elevated. | Repair or replace exhaust fan motor. | No – aesthetic/comfort issue only. | In Progress | CE HVAC
USSPC-FAC-2026-0172 | TRIRIGA-26-12172 | Buckley SFB | 312 | Operations Annex 312 | Rooftop | 2026-02-11 0410Z | USSPACECOM J4 | Routine | Plumbing | 4 | Water hammer occurring in supply piping when fixtures cycle. | Install water hammer arrestors and secure piping supports. | Potential – could impact mission systems if leak reaches equipment. | Submitted | CE Plumbing
USSPC-FAC-2026-0173 | TRIRIGA-26-12173 | Schriever SFB | 302 | Communications Facility 302 | Electrical Room | 2026-02-11 0605Z | USSPACECOM J2 | Urgent | ESS | 3 | Motion sensor PIR detector degraded; detection range reduced. | Replace PIR motion sensor and verify detection coverage. | Yes – loss of backup power to mission facilities. | Submitted | CE ESS
USSPC-FAC-2026-0174 | TRIRIGA-26-12174 | Peterson SFB | 3 | Power Generation Facility 3 | Generator Bay 1 | 2026-02-11 0610Z | USSPACECOM J2 | Routine | Fire Protection | 3 | Clean agent suppression system showing low bottle pressure. | Recharge or replace clean agent suppression bottles. | No – personnel safety and usability concern. | Approved | CE Fire Protection
USSPC-FAC-2026-0175 | TRIRIGA-26-12175 | Buckley SFB | 312 | Operations Annex 312 | Server Closet | 2026-02-11 1045Z | USSPACECOM J6 | Urgent | Electrical | 3 | Power monitoring system reporting harmonics above threshold on critical bus. | Install harmonic filtering or identify harmonic source. | Yes – delayed access to mission operations spaces. | Submitted | CE Electrical
USSPC-FAC-2026-0176 | TRIRIGA-26-12176 | Peterson SFB | 105 | Communications Hub 105 | Antenna Equipment Room | 2026-02-11 1400Z | USSPACECOM J2 | Routine | Electrical | 3 | UPS system reporting degraded battery capacity; estimated runtime below threshold. | Test UPS batteries and replace degraded cells. | No – general facility maintenance. | In Progress | CE Electrical
USSPC-FAC-2026-0177 | TRIRIGA-26-12177 | Schriever SFB | 220 | Mission Support Building 220 | Mechanical Room | 2026-02-11 1455Z | USSPACECOM J6 | Preventive Maintenance | HVAC | 4 | Server room temperature measured at 83°F due to reduced airflow from AHU-5. | Replace filters and clean coils on all air handling units. | No – preventive maintenance. | Scheduled | CE HVAC
USSPC-FAC-2026-0178 | TRIRIGA-26-12178 | Peterson SFB | 105 | Communications Hub 105 | Cable Vault | 2026-02-11 1535Z | USSPACECOM J2 | Emergency | Power Production | 1 | Fuel quality test results indicate water contamination in storage tank. | Drain contaminated fuel, polish tank, and resample. | Yes – affects missile warning operations continuity. | In Progress | CE Power Production
USSPC-FAC-2026-0179 | TRIRIGA-26-12179 | Vandenberg SFB | 77 | Secure Data Facility 77 | Electrical Vault | 2026-02-11 1630Z | USSPACECOM J3 | Routine | Structural | 3 | Retaining wall showing lateral displacement; drainage weeps clogged. | Clear retaining wall weeps and assess lateral stability. | No – personnel safety concern. | Approved | CE Structural
USSPC-FAC-2026-0180 | TRIRIGA-26-12180 | Buckley SFB | 312 | Operations Annex 312 | Rooftop | 2026-02-11 1725Z | USSPACECOM J6 | Routine | Structural | 3 | Roof membrane damage identified during routine walk-down; ponding water present. | Repair roof membrane and address ponding condition. | Yes – impacts launch operations support systems. | Submitted | CE Structural
USSPC-FAC-2026-0181 | TRIRIGA-26-12181 | Vandenberg SFB | 134 | Range Control Facility 134 | Mechanical Room | 2026-02-11 1755Z | USSPACECOM J2 | Urgent | Electrical | 2 | Circuit breaker E-12 will not reset after trip; possible internal fault. | Replace faulty circuit breaker and verify proper operation. | Yes – loss of backup power to mission facilities. | Approved | CE Electrical
USSPC-FAC-2026-0182 | TRIRIGA-26-12182 | Peterson SFB | 198 | Operations Building 198 | Corridor B | 2026-02-11 1800Z | USSPACECOM J2 | Emergency | ESS | 1 | Access control panel communication fault; door status unknown. | Restore communication between access control panel and host. | Yes – impacts real-time telemetry processing. | In Progress | CE ESS
USSPC-FAC-2026-0183 | TRIRIGA-26-12183 | Buckley SFB | 180 | Mission Support Facility 180 | Restroom Corridor | 2026-02-11 1815Z | USSPACECOM J2 | Urgent | Power Production | 2 | Generator ran but did not achieve rated output; voltage droop under load. | Troubleshoot generator output issue and restore rated capacity. | Yes – affects missile warning operations continuity. | In Progress | CE Power Production
USSPC-FAC-2026-0184 | TRIRIGA-26-12184 | Peterson SFB | 198 | Operations Building 198 | Roof | 2026-02-12 0030Z | USSPACECOM J4 | Urgent | Power Production | 2 | Block heater on standby generator non-functional; engine cold. | Repair or replace block heater and verify engine preheat. | Yes – supports satellite uplink equipment. | Completed | CE Power Production | Technician inspected generator and support systems. Identified battery charger rectifier failure. Replaced heater element and verified engine block temperature. Generator started, loaded, and verified at rated output. Transfer tested successfully. | 2026-02-14
USSPC-FAC-2026-0185 | TRIRIGA-26-12185 | Buckley SFB | 180 | Mission Support Facility 180 | Restroom Corridor | 2026-02-12 0110Z | USSPACECOM J2 | Routine | HVAC | 4 | Cooling tower fan motor tripped on overload; condenser water temperature rising. | Repair cooling tower fan motor and test operation. | No – preventive maintenance. | Submitted | CE HVAC
USSPC-FAC-2026-0186 | TRIRIGA-26-12186 | Peterson SFB | 198 | Operations Building 198 | Lobby | 2026-02-12 0540Z | USSPACECOM J3 | Routine | Electrical | 3 | Overheating detected at bus bar connection in electrical room via thermal imaging. | Repair overheating connection and verify with thermal imaging. | Yes – supports satellite command and control systems. | Submitted | CE Electrical
USSPC-FAC-2026-0187 | TRIRIGA-26-12187 | Peterson SFB | 42 | Administrative Building 42 | Roof Access | 2026-02-12 0615Z | USSPACECOM J3 | Urgent | Fire Protection | 2 | Fire alarm notification appliances inaudible in high-ambient-noise areas. | Adjust notification appliance output or add devices for coverage. | Yes – supports space domain awareness operations. | In Progress | CE Fire Protection
USSPC-FAC-2026-0188 | TRIRIGA-26-12188 | Peterson SFB | 105 | Communications Hub 105 | Ground Floor Lobby | 2026-02-12 0750Z | USSPACECOM J3 | Routine | Fire Protection | 3 | Fire alarm pull station damaged at egress point; device non-functional. | Replace damaged fire alarm pull station. | Yes – supports space domain awareness operations. | Approved | CE Fire Protection
USSPC-FAC-2026-0189 | TRIRIGA-26-12189 | Peterson SFB | 145 | Operations Building 145 | Conference Room 3 | 2026-02-12 0925Z | USSPACECOM J3 | Routine | ESS | 4 | Card reader database sync failure; stale credential data. | Resolve database sync issue and verify credential data. | No – quality of life issue; no mission degradation. | In Progress | CE ESS
USSPC-FAC-2026-0190 | TRIRIGA-26-12190 | Buckley SFB | 312 | Operations Annex 312 | Server Closet | 2026-02-12 1005Z | USSPACECOM J3 | Urgent | Power Production | 3 | Generator ran but did not achieve rated output; voltage droop under load. | Troubleshoot generator output issue and restore rated capacity. | Yes – affects classified processing environment. | In Progress | CE Power Production
USSPC-FAC-2026-0191 | TRIRIGA-26-12191 | Peterson SFB | 42 | Administrative Building 42 | Main Office | 2026-02-12 1200Z | USSPACECOM J3 | Urgent | Fire Protection | 3 | Fire alarm pull station damaged at egress point; device non-functional. | Replace damaged fire alarm pull station. | No – personnel safety and usability concern. | Submitted | CE Fire Protection
USSPC-FAC-2026-0192 | TRIRIGA-26-12192 | Buckley SFB | 312 | Operations Annex 312 | Ops Floor | 2026-02-12 1830Z | USSPACECOM J3 | Routine | Plumbing | 4 | Domestic water pressure low throughout facility; measured at 42 PSI vs 60 PSI normal. | Investigate low water pressure and restore to normal. | No – aesthetic/comfort issue only. | Completed | CE Plumbing | Responded and isolated affected section. Discovered dried-out P-trap in floor drain. Replaced mixing valve and set to 120°F output. Flow verified at all fixtures. Area cleaned and restored. | 2026-02-27
USSPC-FAC-2026-0193 | TRIRIGA-26-12193 | Peterson SFB | 210 | Operations Building 210 | Mechanical Penthouse | 2026-02-12 2035Z | USSPACECOM J4 | Routine | Power Production | 4 | Fuel quality test results indicate water contamination in storage tank. | Drain contaminated fuel, polish tank, and resample. | No – aesthetic/comfort issue only. | Approved | CE Power Production
USSPC-FAC-2026-0194 | TRIRIGA-26-12194 | Vandenberg SFB | 134 | Range Control Facility 134 | Exterior HVAC Pad | 2026-02-12 2205Z | USSPACECOM J6 | Preventive Maintenance | Power Production | 4 | Quarterly fuel sampling and polishing service. | Collect fuel samples and perform polishing as needed. | No – preventive maintenance. | In Progress | CE Power Production
USSPC-FAC-2026-0195 | TRIRIGA-26-12195 | Buckley SFB | 312 | Operations Annex 312 | Secure Entry Vestibule | 2026-02-12 2340Z | USSPACECOM J6 | Urgent | ESS | 3 | Duress alarm button at post 1 non-functional during test. | Replace duress alarm switch and test signaling. | Yes – degrades ground station equipment reliability. | In Progress | CE ESS
USSPC-FAC-2026-0196 | TRIRIGA-26-12196 | Buckley SFB | 180 | Mission Support Facility 180 | Restroom Corridor | 2026-02-13 0645Z | USSPACECOM J6 | Preventive Maintenance | Power Production | 4 | Scheduled monthly generator run test and inspection. | Perform annual load bank test and full PM service. | No – preventive maintenance. | Scheduled | CE Power Production
USSPC-FAC-2026-0197 | TRIRIGA-26-12197 | Buckley SFB | 312 | Operations Annex 312 | Ops Floor | 2026-02-13 0740Z | USSPACECOM J2 | Emergency | Electrical | 2 | Circuit breaker E-10 will not reset after trip; possible internal fault. | Replace faulty circuit breaker and verify proper operation. | Yes – intermittent loss of operator consoles. | Completed | CE Electrical | Arrived on-site, performed lockout/tagout, and investigated. Found loose connection at breaker lug causing arcing. Replaced GFI breaker and verified trip function. All circuits tested and verified. Arc flash labels updated. | 2026-02-13
USSPC-FAC-2026-0198 | TRIRIGA-26-12198 | Peterson SFB | 3 | Power Generation Facility 3 | Transfer Switch Room | 2026-02-13 0930Z | USSPACECOM J6 | Preventive Maintenance | ESS | 4 | Scheduled annual electronic security system testing and certification. | Inspect access control hardware and repair or replace reader. | No – preventive maintenance. | Scheduled | CE ESS
USSPC-FAC-2026-0199 | TRIRIGA-26-12199 | Buckley SFB | 180 | Mission Support Facility 180 | Mechanical Room | 2026-02-13 0945Z | USSPACECOM J6 | Preventive Maintenance | Power Production | 4 | Quarterly fuel sampling and polishing service. | Investigate capacity loss and perform corrective maintenance. | No – preventive maintenance. | Approved | CE Power Production
USSPC-FAC-2026-0200 | TRIRIGA-26-12200 | Vandenberg SFB | 51 | Launch Operations Building 51 | Equipment Room | 2026-02-13 0955Z | USSPACECOM J6 | Routine | Electrical | 3 | Transformer humming abnormally; oil temperature gauge reading high. | Inspect transformer; sample oil and assess condition. | Yes – affects continuous space surveillance mission. | Submitted | CE Electrical